- ANNEX 5

MODEL START-UP PROGRAMME ESTIMATE

(PARTNER COUNTRY) ……………….	EUROPEAN DEVELOPMENT

MINISTRY     ……………….	FUND/GENERAL BUDGET 	OF THE EUROPEAN UNION

- PROJECT …………………………

- CENTRAL/PUBLIC COMMISSIONED OPERATIONS (please specify)

- GLOBAL/INDIVIDUAL FINANCIAL/BUDGETARY COMMITMENT No ………… (accounting number)

- PROGRAMME ESTIMATE

- START-UP PERIOD

- FROM ........................ TO ........................

Total amount of the budget (imprest component) of start-up programme estimate in (EUR/other currency please specify):

…………………………………………………………………………………………….

The full accounting number must be quoted in all correspondence and on all financial documents.

CONTENTS

1.	WORK PROGRAMME	3

1.1.	Introduction	3

1.2.	Activities	3

1.3.	Implementation	3

1.3.1.	Material and non-material means	4

1.3.2.	Organisation	4

1.3.3.	Special conditions	4

2.	BUDGET AND FINANCING PLAN	4

3.	TECHNICAL AND ADMINISTRATIVE IMPLEMENTING ARRANGEMENTS	5

3.1.	Management structure	5

3.2.	Imprest administrator and imprest accounting officer	6

3.3.	Period covered	7

3.4.	Amount of the budget of the start-up programme estimate	7

3.5.	“Start-up programme estimate” bank account	8

3.6.	Pre-financing	8

3.7.	Eligible expenditure	9

3.8.	Supporting documents	9

3.9.	Public contract award procedures	10

3.10.	Cash disbursement procedures	10

3.11.	Staff management	11

3.12.	Implementation reports	11

3.13.	Closure of the start-up programme estimate	12

3.14.	Tax and customs arrangements	12

3.15.	Other matters to be specified	12

4.	SIGNATURES	13

5.	ANNEXES	14

# WORK PROGRAMME

## Introduction

This section is intended to put the start-up programme estimate activities in their context and describe their purpose.

As background, give a short summary of the project objectives and purpose with reference to the financing agreement concerned and describe the general context and proposed operations.

The sole purpose of the start-up programme estimate is to finance the work of launching the project or programme and of preparing the multiannual operational programme estimate.

The preparation tasks mainly involve:

- drawing up the logical framework;

- preparing the detailed work programme;

- drawing up the provisional implementation timetable;

- preparing the detailed budget and financing plan;

- drawing up the technical and administrative implementing arrangements.

These tasks will be carried out on the basis, inter alia, of:

- consultations with the national (or regional) authorities concerned, the Delegation of the European Union and any parties involved at various stages of project implementation;

- reference documents and preliminary studies carried out at the project  formulation stage.

## Activities

Describe here the activities that will be implemented under the start-up programme estimate.

The activities to be implemented under this start-up programme estimate to prepare for the operational programme estimate are:

1.	………………………………………………………………..………………

2.	………………………………………………………………………..………

3.	………………………………………………………………………………..

## Implementation

This part describes the material and human means needed to carry out the start-up programme estimate, plus relevant details of internal organisation and the conduct of activities.

### Material and non-material means

Describe here the material and non-material means that will be used to implement the start-up programme estimate. Account for the means required for each activity.

### Organisation

Indicate:

- the contracting authority, which will be the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer or public commissioned body;

- where appropriate, the project supervisor.

### Special conditions

Mention any conditions to be met or any accompanying measure to be taken prior to or during the project by the government or the supervisory authority. Set out a timetable for these measures.

# BUDGET AND FINANCING PLAN

Since the sole purpose of the start-up programme estimate is to finance during a limited period of time the setup costs of the project and of the activities needed to draw up the operational programme estimate, the budget should not make as a rule provision for investments or contingencies. However, if needed, provision for investments should be of a minor amount.

The budget given below for this start-up programme estimate summarises the estimated costs of implementing the start-up programme estimate without giving a detailed breakdown.

The detailed estimate of costs (detailed budget) is attached at Annex (...) to this start-up programme estimate. It should be presented in the form of detailed tables backed up by calculation notes.

The table below shows the estimate of all the expenditure planned under the start-up programme estimate (by activity, investment costs, if applicable, and operating costs), broken down according to each donor's contribution.

The titles and breakdown of specific activities and other expenditure in the table below are given by way of example. You may usefully refer to instructions for drawing up a budget in the example for an operational  programme estimate in Annex 4 to the PE Guide.

|  | Activities and other costs | EDF/EU contribution | Contribution of the partner country | Other contributions | TOTAL |
| --- | --- | --- | --- | --- | --- |
| 1. | Activities |  |  |  |  |
| 1.1 | Activity 1 |  |  |  |  |
| 1.2 | Activity 2 |  |  |  |  |
| 1.3 | Activity 3 |  |  |  |  |
|  | Subtotal |  |  |  |  |
| 2. | Investment costs |  |  |  |  |
| 2.1 | Equipment |  |  |  |  |
| 2.2 | Supplies |  |  |  |  |
|  | Subtotal |  |  |  |  |
| 3. | Operating costs |  |  |  |  |
| 3.1 | Staff costs |  |  |  |  |
| 3.2 | Office rental |  |  |  |  |
| 3.3 | Office operating costs |  |  |  |  |
| 3.4 | Vehicle operating costs |  |  |  |  |
|  | Subtotal |  |  |  |  |
| 4. | Bank charges and exchanges differences |  |  |  |  |
|  | TOTAL |  |  |  |  |

# TECHNICAL AND ADMINISTRATIVE IMPLEMENTING ARRANGEMENTS

The technical and administrative implementing arrangements of this start-up programme estimate must comply with the rules and procedures set out in the annexed “practical guide to procedures for programme estimates ” (hereinafter referred to as the "PE Guide").

This section gives more detailed and additional information on some of the arrangements for this start-up programme estimate.

## Management structure

In case of central operations:

Under the provisions of the corresponding financing agreement, the project has technical and financial autonomy to manage the resources allocated to it for the budget of this start-up programme estimate.

The budget will be implemented by the imprest administrator and imprest accounting officer named below under point 3.2.

- In case of public commissioned operations:

Under the provisions of the corresponding financing agreement and of the corresponding implementation agreement the project is managed and implemented by the following body:

………....................................................................... (specify).

The budget will be implemented by an imprest administrator and an imprest accounting officer to be designated by that body named below under point 3.2.

If applicable, set out the role and specific responsibilities of the body (a) in the phases prior to award of contracts and grants financed with specific individual financial/budgetary commitments and (b) in supervising their implementation. Specify also if procurement contracts and grants will be signed in the name of the commissioned body or in the name of the partner country.

## Imprest administrator and imprest accounting officer

In case of central operations:

For implementation of the budget, the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer partially delegates his/her powers to the imprest administrator and imprest accounting officer designated below.

- In case of public commissioned operations:

For implementation of the budget of this start-up programme estimate, the partner country designates a body governed by public law or a body governed by private law with a public-service. To this end the body authorises the imprest administrator and imprest accounting officer designated below to act in its name and in the name of the partner country.

- In all cases:

This partial delegation of powers is conditional upon:

- strict observance of the rules and procedures set out in the PE Guide and in this start-up programme estimate;

- deposit of the authorised signatures of the imprest administrator and imprest accounting officer;

- opening of a bank account, that require(s) two signatures, that of the imprest administrator and that of the imprest accounting officer.

- The designated imprest administrator is: (name and position) …………………….

- The designated imprest accounting officer is: (name and position) ……………...

The tasks and responsibilities of the imprest administrator and imprest accounting officer are described in the PE Guide. Any additional tasks expected of them in the course of the programme estimate implementation should be mentioned here.

## Period covered

The period covered by this start-up programme estimate runs from ……………………… to ………………………, i.e. …… months.

Payments under the budget of this start-up programme estimate can only be made for expenditure linked to activities properly scheduled during this period and used solely for task of preparing the multiannual operational programme estimate.

No further expenditure may be committed after the end of this period unless the expenditure is covered by the approved budget of the multiannual operational programme estimate consecutive to the start-up.

Expenditure paid and/or committed before the date on which this start-up programme estimate is endorsed by the Head of Delegation will, on no account, be covered by the EDF/Budget.

## Amount of the budget of the start-up programme estimate

The total amount of the budget is:

(EUR/other currency please specify)… … … …… …… …… …… ………………………………

If applicable:

part to be carried out in other currency:

(other currency) … …… …… ……… ……… …… ……………………

part to be carried out in EUR:

(EUR)…………………..…………………………………

## “Start-up programme estimate” bank account

The references for the “start-up programme estimate” bank account that require(s) two signatures, that of the imprest administrator and that of the imprest accounting officer, are as follows:

Account in (EUR/other currency please specify)

- Bank: ……………………………………………………………………

- Name: …………………………………………………………………….

- Account No: ………………………………………………………………

Add the references of another account if any:

- Account in (EUR/other currency please specify)

- Bank: ……………………………………………………………………

- Name: …………………………………………………………………….

- Account No: ………………………………………………………………

## Pre-financing

Upon the start-up programme estimate's signature by all parties and registration of the pre-financing request, the payment (single payment) shall be provided within 60 calendar days for EDF and 30 calendar days for programme estimates financed under the EU Budget.

The amount of the pre-financing that will be paid into the bank account in the currency of the start-up programme estimate referred to above, is set at 100% of the budget, i.e.:

(EUR/ other currency, please specify) ………………………………………………………………

Add the references of another account if any:

- Account in (EUR/other currency please specify)

- Bank: ……………………………………………………………………

- Name: …………………………………………………………………….

- Account No: ………………………………………………………………

## Eligible expenditure

Eligible costs are actual costs incurred by the partner country/commissioned body and which:

a)	are incurred during the implementation phase of the start-up programme estimate;

- costs relating to services and works shall relate to activities performed during the implementation phase of the programme estimate. Costs relating to supplies shall relate to delivery and installation of items during the implementation phase of the programme estimate. Signature of a contract, placing of an order, or entering into any commitment for expenditure within the implementation phase for future delivery of services, works or supplies after expiry of the implementation phase do not meet this requirement. Cash transfers between the partner country, the commissioned body and/or other entities may not be considered as costs incurred;

- expenditure incurred during the implementation phase shall be paid in the implementation phase;

- an exception is made for the possible expenses applied by the bank for the opening of the account(s) and/or for the validation of the form(s) for the “financial identification” (see section 3.1.1. of this PE Guide);

b)	are indicated in the overall budget of the start-up programme estimate;

c)	are necessary for the implementation of the start-up programme estimate;

d)	are identifiable and verifiable, in particular being recorded in the accounting records of the partner country / commissioned body and determined in accordance with the accounting standards and the usual cost accounting practices applicable to the partner country / commissioned body;

e)	comply with the requirements of applicable tax and social legislation;

f)	are reasonable, justified and comply with the requirements of sound financial management, in particular regarding economy and efficiency.

## Supporting documents

The supporting documents will be checked by an external auditor during the first expenditure verification carried out after the first 12 months period of the operational programme estimate and included in the first full financial report.

Therefore, when submitting the first full financial report (covering the period of the start-up and the first 12 months of the operational programme estimate), for the justification of the start-up pre-financing to the Head of Delegation the original supporting documents will not be attached to the corresponding requests but will be made available for consultation if requested by the Delegation.

The imprest administrator and the imprest accounting officer shall ensure that a logical system of filing and record retention in line with the applicable legal norms and a reliable and easy to follow audit trail are put in place.

## Public contract award procedures

As the start-up programme estimate is normally aimed at preparing the operational programme estimate, it should not involve the award of procurement contracts or grants. On the contrary, insert:

The table summarising the powers delegated by the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer for procurement contract procedures is set out in Annex (...) of this programme estimate. (See table in Annex 13 to the PE Guide. The amounts should be mentioned in the currency of the implementation of the programme estimate).

In case the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer and the Head of Delegation decide with one accord to lower the award thresholds, the new one must be specified here in the currency of the implementation of the start-up programme estimate.

Decisions concerning the award of public contracts must be referred for authorisation to the Head of Delegation. Depending on the choice of the Head of Delegation, add “, excluding decisions related to the award of public contracts worth up to the equivalent of EUR 100,000 or lower threshold (specify currency and exact amount)”

Where ex ante control of the contract procedures by the European Commission is strengthened: Moreover, decisions related to the contract procedures, particularly (indicate the relevant steps), must also be referred for authorisation to the Head of Delegation.

Where the contracting authority from the partner country may use its own rules and procedures for procurement delete the four preceding paragraphs and insert: "The contracting authorities applies its positively-assessed rules and procedures for procurement for contracts covered by the budget. No ex ante-control will be carried out in this regard."

Please insert a description of or a reference to the applicable rules and procedures.

## Cash disbursement procedures

Payments will be made for and on behalf of the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer from the “start-up programme estimate” bank account referred to in section 3.5. These transactions do not require the intervention of the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer or the Head of Delegation.

The relevant representative of the partner country(ies)/National (or Regional) Authorising Officer, in agreement with the Head of Delegation, may decide to fix a threshold above which all payments need his or her prior authorisation. If so, this threshold and any implementing conditions must be specified here.

For payments in foreign exchange, the rules for the use of the currencies to make payments must be described here when they differ from or supplement the rules set out in Annex 6 to the PE Guide.

If necessary, petty cash in national currency may be kept to pay sundry administrative expenditure. The petty cash will be managed under the responsibility of the imprest accounting officer.

## Staff management

Set out the rules for staff management covering seconded officials or other agents of the partner country concerned, contract staff and any other types of staff employed for the project. The rules must include, or refer to, procedures for seconding or recruiting staff, national legislation in force on the subject, the type of contract used and related entitlements (social security, insurance, etc.).

A list of staff, references to/texts of the rules in force, a copy of the standard contract for contract staff, pay scales, rates for additional allowances and for daily mission allowances can be found in Annex (...) to this start-up programme estimate.

## Implementation reports

The imprest administrator and the imprest accounting officer must draw up a comprehensive final implementation report and the full financial report.

- The comprehensive final implementation report must be submitted at the latest 60 days after the end of the period covered by the start-up programme estimate

- The full financial report is a document required for the justification of the pre-financing received and it shall be submitted at the end of the first 12 months period of the operational programme estimate together with the expenditure verification report, which in this case will cover the period from the beginning of the start-up programme estimate until the end of the first 12 months period of the operational programme estimate.

____ copies of the reports must be submitted to the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer, ____ copies to the supervisory technical Ministry (where applicable) and ____ copies to the Head of Delegation.

## Closure of the start-up programme estimate

The start-up programme estimate closure will be integrated in the closure of the operational programme estimate whereas the clearing of the start-up pre-financing will be executed at the same time of the operational programme estimate's  first pre-financing clearing, when the Commission receives the expenditure verification and the full financial reports for the period covering from the first day of the start-up programme estimate and the first 12 months period of the operational programme estimate.

In case the expenditure verification has detected amounts corresponding to ineligible expenditure, the further pre-financing of the operational programme estimate will be reduced accordingly, proportionally to the seriousness of the findings.

The balance of the “start up programme estimate” bank account shall be transferred and used for the operational implementation of the operational programme estimate, using the same bank account opened for the start-up programme estimate.

Expenditure verification

- The expenditure verification by an external auditor (not directly linked to the request of payment) will be carried out  at the same time as the first 12 months period of the operational programme estimate expenditure verification. This contract, financed through specific commitment,  is concluded and managed by the European Commission for and on behalf of the partner country(ies) concerned.

- The objective of the expenditure verification is for the Auditor to carry out specific verification procedures which are listed in the terms of reference and to submit to the European Commission expenditure verification reports.

## Tax and customs arrangements

For the EDF only:

The tax and customs arrangements are those set out in Article 31 of Annex IV to the Cotonou Agreement as well as in the general conditions of the financing agreement.

For the Budget only:

The tax and customs arrangements are those set out in the general conditions of the financing agreement.

## Other matters to be specified

# SIGNATURES

For central  operations

The imprest administrator	The imprest accounting officer

for agreement	for agreement

For public commissioned operations

Indicate the body or entity mentioned in section 3.2, represented by:

The Imprest Administrator	The Imprest Accounting Officer
For agreement	For agreement

(name and position)	(name and position)

(date and signature)	(date and signature)

The technical ministry (if applicable)

for agreement

(exact title)

(name and position)

(date and signature)

The relevant representative of the	The Head of Delegation

partner country(ies)/National

(or Regional) Authorising Officer

for authorisation	for endorsement

(name and position)	(name)

(date and signature)	(date and signature)

# ANNEXES

All the Annexes to this start-up programme estimate are an integral part thereof. They have the same force as the start-up programme estimate itself.

Annex 1:	Practical guide to procedures for programme estimates

Annex 2:	Detailed budget

Annex 3:	Summary table of powers delegated by the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer for contract award procedures

- Annex 4:	Staff management documents

Standard employment contract or work contract (fixed term)

National social security rules

Staff list

Pay scales

Rates for additional allowances

Rates for mission daily allowances

Other relevant documents

- Annex 5:	Financial identification form (if needed)

- Other annexes

- Annex 3:	Detailed budget

The purpose of this Annex is to present the budget in enough detail for the relevant representative of the partner country(ies)/the National (or Regional) Authorising officer and the Head of Delegation to understand and authorise it.

List separately: estimated expenditure for carrying out the planned activities and sub-activities; investment expenditure; project operating expenditure.

- EXAMPLE OF DETAILED BUDGET TABLE

|  | Activities and other costs | EDF/EU contribution | Contribution of the partner country | Other contributions | TOTAL |
| --- | --- | --- | --- | --- | --- |
| 1. | Activities |  |  |  |  |
| 1.1 | Activity 1 |  |  |  |  |
| 1.1.1 | Subactivity 1.1. |  |  |  |  |
| 1.1.2 | Subactivity 1.2. |  |  |  |  |
| 1.2 | Activity 2 |  |  |  |  |
| 1.3 | Activity 3 |  |  |  |  |
|  | Subtotal |  |  |  |  |
| 2. | Investment costs |  |  |  |  |
| 2.1 | Equipment |  |  |  |  |
| 2.2 | Supplies |  |  |  |  |
|  | Subtotal |  |  |  |  |
| 3. | Operating costs |  |  |  |  |
| 3.1 | Staff costs |  |  |  |  |
| 3.2 | Office rental |  |  |  |  |
| 3.3 | Office operating costs |  |  |  |  |
| 3.4 | Vehicle operating costs |  |  |  |  |
|  | Subtotal |  |  |  |  |
| 4. | Bank charges and exchanges differences |  |  |  |  |
|  | TOTAL |  |  |  |  |

Given the absence of specific commitments in a start-up PE, no reference to imprest component as such is used in the template for start-up PE, and budget is used instead.

The start date may not be prior to the date of signature of the programme estimate by the relevant representative of the partner country(ies)/National (or Regional) Authorising Officer and endorsement by the Head of Delegation. The date of endorsement is the trigger date for expenditure becoming eligible under the EDF/Budget.

The maximum duration of the start-up programme estimate is four months.

With the only exception of the possible expenses applied by the bank for the opening of the account(s) and/or for the validation of the form(s) for the “financial identification” (see section 3.1.1. of this PE Guide).

The same bank account shall be used for the consecutive multiannual operational programme estimate.

An electronic copy of the scanned supporting documents shall be attached to the full financial report

(See PE Guide point 3.1.4 Documentation, filing and record keeping and Annex 10 to the PE Guide: Examples of supporting documents by type of expenditure to be included in the full financial report).

See Annex 8 of the PE Guide.